## Gantchart
GANTT CHART | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
Developing Chat Server For Addressing FAQ’s about Creative Learning | [6 empty] | AP Shah Institute of Technology - Information Technology
Prof. Anagha Aher | [6 empty] | DATE | [6 empty] | 2023-05-04
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Research paper search | Shridhar Joshi | 2022-07-29 | 2022-08-12 | 3 | 100% | bar: WEEK 1 F to WEEK 2 T
1.1.1 | Research paper finalization | Akshada Warik | 2022-08-12 | 2022-08-26 | 3 | 100% | bar: WEEK 2 W
1.2 | Project Title | Shridhar Joshi, Akshada Warik, Harsh Rathod | 2022-08-12 | 2022-08-26 | 3 | 100% | bar: WEEK 2 W to WEEK 3 W
1.3 | Abstract | Shridhar Joshi | 2022-08-19 | 2022-08-26 | 1 | 100% | bar: WEEK 2 R to WEEK 3 R
1.4 | Objectives | Akshada Warik | 2022-08-26 | 2022-09-02 | 1 | 100% | bar: WEEK 3 M to WEEK 3 R
1.5 | Literature Review | Harsh Rathod | 2022-09-02 | 2022-09-09 | 1 | 100% | bar: WEEK 3 T to WEEK 3 R
1.6 | Problem Definition | Shridhar Joshi, Akshada Warik, Harsh Rathod | 2022-09-09 | 2022-09-23 | 1 | 100% | bar: WEEK 3 F
1.7 | Scope | Akshada Warik | 2022-09-16 | 2022-09-23 | 1 | 100% | bar: WEEK 3 F
1.8 | Technology stack | Shridhar Joshi, Akshada Warik, Harsh Rathod | 2022-09-23 | 2022-09-30 | 1 | 100% | bar: WEEK 3 F
1.9 | Benefits for environment | Akshada Warik | 2022-09-30 | 2022-10-07 | 1 | 100% | bar: WEEK 3 F
1.1 | Benefits for society | Harsh Rathod | 2022-10-07 | 2022-10-14 | 1 | 100% | bar: WEEK 3 F
1.11 | Applications | Shridhar Joshi | 2022-10-14 | 2022-10-21 | 1 | 100% | bar: WEEK 3 F
2 | Project Design
2.1 | Proposed System | Shridhar Joshi, Akshada Warik, Harsh Rathod | 2023-01-18 | 2023-02-08 | 1 | 100% | bar: WEEK 4 M to WEEK 4 R
2.2 | Design(Flow Of Modules) | Shridhar Joshi | 2023-02-09 | 2023-02-16 | 1 | 100% | bar: WEEK 4 F to WEEK 5 F
2.3 | Activity Diagram | Shridhar Joshi | 2023-02-16 | 2023-02-23 | 1 | 100%
2.4 | Use Case Diagram | Akshada Warik | 2023-03-02 | 2023-03-09 | 1 | 100%
2.5 | Description Of Use Case | Harsh Rathod | 2023-03-09 | 2023-03-16 | 1 | 100%
2.6 | Modules | Shridhar Joshi, Akshada Warik, Harsh Rathod | 2023-03-16 | 2023-03-23 | 1 | 100%
2.6.1 | Module-1 |  | 2023-03-23 | 2023-03-30 | 1 | 100%
2.6.2 | Module-2 |  | 2023-04-05 | 2023-04-12 | 1 | 100%
2.6.3 | Module-3 |  | 2023-04-13 | 2023-04-20 | 1 | 100%
2.6.4 | Module-4 |  | 2023-04-20 | 2023-04-27 | 1 | 100%
2.7 | Preparation Of Report |  | 2023-04-27 | 2023-05-04 | 1 | 100%
3 | Project Implementation
3.1 | Module-1 | Shridhar Joshi |  |  | 0 | 0%
3.2 | Module-2 | Shridhar Joshi, Harsh Rathod |  |  | 0 | 0%
3.3 | Module-3 | Harsh Rathod, Akshada Warik |  |  | 0 | 0%
3.4 | Module-4 | Akshada Warik |  |  | 0 | 0%
4 | Testing
4.1 | Design of Test Cases | Shridhar Joshi, Akshada Warik, Harsh Rathod | 2022-07-29 | 2022-08-12 | 3 | 0% | bar: WEEK 1 T to WEEK 1 F; WEEK 2 T to WEEK 2 F; WEEK 3 T to WEEK 3 F
4.2 |  | Shridhar Joshi, Akshada Warik, Harsh Rathod | 2022-08-12 | 2022-08-26 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.3 |  | Shridhar Joshi, Akshada Warik, Harsh Rathod | 2022-08-12 | 2022-08-26 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.4 |  | Shridhar Joshi, Akshada Warik, Harsh Rathod | 2022-08-19 | 2022-08-26 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.5 |  | Shridhar Joshi, Akshada Warik, Harsh Rathod | 2022-08-26 | 2022-09-02 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.6 |  | Shridhar Joshi, Akshada Warik, Harsh Rathod | 2022-09-02 | 2022-09-09 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.7 |  | Shridhar Joshi, Akshada Warik, Harsh Rathod | 2022-09-09 | 2022-09-23 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.8 |  | Shridhar Joshi, Akshada Warik, Harsh Rathod | 2022-09-16 | 2022-09-23 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.9 |  | Shridhar Joshi, Akshada Warik, Harsh Rathod | 2022-09-23 | 2022-09-30 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.1 |  | Shridhar Joshi, Akshada Warik, Harsh Rathod | 2022-09-30 | 2022-10-07 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.1 |  | Shridhar Joshi, Akshada Warik, Harsh Rathod | 2022-10-07 | 2022-10-14 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.1 |  | Shridhar Joshi, Akshada Warik, Harsh Rathod | 2023-01-18 | 2022-10-21 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.1 |  | Shridhar Joshi, Akshada Warik, Harsh Rathod | 2023-02-09 | 2023-02-08 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.1 |  | Shridhar Joshi, Akshada Warik, Harsh Rathod | 2023-02-16 | 2023-02-16 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.1 |  | Shridhar Joshi, Akshada Warik, Harsh Rathod | 2023-03-02 | 2023-02-23 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.1 |  | Shridhar Joshi, Akshada Warik, Harsh Rathod | 2023-03-09 | 2023-03-09 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.1 |  | Shridhar Joshi, Akshada Warik, Harsh Rathod | 2023-03-16 | 2023-03-16 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.1 |  | Shridhar Joshi, Akshada Warik, Harsh Rathod | 2023-03-23 | 2023-03-23 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.1 |  | Shridhar Joshi, Akshada Warik, Harsh Rathod | 2023-04-05 | 2023-03-30 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.1 |  | Shridhar Joshi, Akshada Warik, Harsh Rathod | 2023-04-13 | 2023-04-12 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
5.2 | Graphical Representation | Y | 2023-04-20 | 2023-04-20 | 0 | 0%
5.3 | Report Preparation |  | 2023-04-27 | 2023-04-27