## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | Go-Brainous: An AI Based Educational App for Kid's |  |  |  |  | INSTUTUTE & DEPARTMENT NAME | [6 empty] | AP Shah Institute of Technology, IT Department
PROJECT GUIDE |  | Prof. Roshna Sangle |  |  |  |  | DATE | [6 empty] | 2023-04-13
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Research paper search | Bhimraj Parihar | 2022-07-29 | 2022-08-12 | 3 | 100% | bar: WEEK 1 F to WEEK 2 T; WEEK 5 R to WEEK 5 F
1.1.1 | Research paper finalization | Siddharth Chhoriya | 2022-07-29 | 2022-08-12 | 3 | 100% | bar: WEEK 2 W; WEEK 5 R to WEEK 5 F
1.2 | Project Title | Bhimraj Parihar, Siddharth Chhoriya | 2022-07-29 | 2022-08-12 | 3 | 100% | bar: WEEK 2 W to WEEK 3 W; WEEK 5 R to WEEK 5 F
1.3 | Abstract | Bhimraj Parihar | 2022-08-26 | 2022-09-06 | 1 | 100% | bar: WEEK 2 R to WEEK 3 R; WEEK 5 R to WEEK 5 F
1.4 | Objectives | Siddharth Chhoriya | 2022-08-26 | 2022-09-06 | 1 | 100% | bar: WEEK 3 M to WEEK 3 R; WEEK 5 R to WEEK 5 F
1.5 | Literature Review | Bhimraj Parihar | 2022-08-26 | 2022-09-06 | 1 | 100% | bar: WEEK 3 T to WEEK 3 R; WEEK 5 R to WEEK 5 F
1.6 | Problem Definition | Bhimraj Parihar, Siddharth Chhoriya | 2022-08-26 | 2022-09-06 | 1 | 100% | bar: WEEK 3 F; WEEK 5 R to WEEK 5 F
1.7 | Scope | Siddharth Chhoriya | 2022-08-26 | 2022-09-06 | 1 | 100% | bar: WEEK 3 F; WEEK 5 R to WEEK 5 F
1.8 | Technology stack | Siddharth Chhoriya, Bhimraj Parihar | 2022-08-26 | 2022-09-06 | 1 | 100% | bar: WEEK 3 F; WEEK 5 R to WEEK 5 F
1.9 | Benefits for environment | Siddharth Chhoriya | 2022-08-26 | 2022-09-06 | 1 | 100% | bar: WEEK 3 F; WEEK 5 R to WEEK 5 F
1.1 | Benefits for society | Siddharth Chhoriya | 2022-08-26 | 2022-09-06 | 1 | 100% | bar: WEEK 3 F; WEEK 5 R to WEEK 5 F
1.11 | Applications | Bhimraj Parihar | 2022-08-26 | 2022-09-06 | 1 | 100% | bar: WEEK 3 F; WEEK 5 R to WEEK 5 F
2 | Project Design
2.1 | Proposed System | Bhimraj Parihar, Siddharth Chhoriya | 2022-09-30 | 2022-10-07 | 1 | 100% | bar: WEEK 4 M to WEEK 4 R; WEEK 5 R to WEEK 5 F
2.2 | Design(Flow Of Modules) | Bhimraj Parihar | 2022-09-30 | 2022-10-07 | 1 | 100% | bar: WEEK 4 T to WEEK 6 R
2.3 | Activity Diagram | Bhimraj Parihar | 2022-09-30 | 2022-10-07 | 1 | 100% | bar: WEEK 4 R to WEEK 5 F
2.4 | Use Case Diagram | Siddharth Chhoriya | 2022-09-30 | 2022-10-07 | 1 | 100% | bar: WEEK 5 M to WEEK 6 F
2.5 | Description Of Use Case | Siddharth Chhoriya | 2022-09-30 | 2022-10-07 | 1 | 100% | bar: WEEK 5 M to WEEK 6 F
2.6 | splash Screen & Home Page | Bhimraj Parihar, Siddharth Chhoriya | 2022-09-30 | 2022-10-07 | 1 | 100% | bar: WEEK 5 T to WEEK 5 R
2.6.1 | Adding Games | Bhimraj Parihar | 2022-09-30 | 2022-10-07 | 1 | 100% | bar: WEEK 5 W to WEEK 6 F
2.6.2 | Tensorflow lite Model | Bhimraj Parihar | 2022-09-30 | 2022-10-07 | 1 | 100% | bar: WEEK 5 W to WEEK 6 R
2.6.3 | Settings | Bhimraj Parihar | 2022-09-30 | 2022-10-07 | 1 | 100% | bar: WEEK 5 W to WEEK 6 W
2.6.4 | Drawing pad | Siddharth Chhoriya | 2022-09-30 | 2022-10-07 | 1 | 100% | bar: WEEK 5 R to WEEK 6 F
2.7 | Preparation Of Report | Bhimraj Parihar, Siddharth Chhoriya | 2022-09-30 | 2022-10-07 | 1 | 100% | bar: WEEK 5 R to WEEK 5 F; WEEK 6 F
3 | Project Implementation
3.1 | splash Screen & Home Page | Bhimraj Parihar | 2022-10-02 | 2022-10-10 | 0 | 100% | bar: WEEK 5 R to WEEK 5 F; WEEK 7 M to WEEK 9 M
3.2 | Adding Games | Bhimraj Parihar | 2022-10-11 | 2022-10-20 | 0 | 100% | bar: WEEK 5 R to WEEK 5 F; WEEK 8 M to WEEK 9 F
3.3 | Tensorflow lite Model | Bhimraj Parihar | 2022-10-21 | 2022-10-30 | 0 | 100% | bar: WEEK 5 R to WEEK 5 F; WEEK 9 M to WEEK 9 F
3.4 | Settings | Siddharth Chhoriya | 2022-11-01 | 2022-11-10 | 0 | 100% | bar: WEEK 5 R to WEEK 5 F; WEEK 7 R to WEEK 9 F
3.4 | Drawing pad | Siddharth Chhoriya | 2022-11-01 | 2022-11-10 | 0 | 100% | bar: WEEK 5 R to WEEK 5 F; WEEK 9 M to WEEK 9 F
4 | Testing
4.1 | Design of Test Cases | Bhimraj Parihar, Siddharth Chhoriya | 2023-01-18 | 2023-01-24 | 3 | 100% | bar: WEEK 5 R to WEEK 5 F; WEEK 10 M
4.2 | Question Creation Component Test | Bhimraj Parihar, Siddharth Chhoriya | 2023-01-27 | 2023-02-03 | 1 | 100% | bar: WEEK 5 R to WEEK 5 F; WEEK 10 M to WEEK 10 T
4.3 | Splash Screen | Bhimraj Parihar, Siddharth Chhoriya | 2023-02-04 | 2023-02-10 | 1 | 100% | bar: WEEK 5 R to WEEK 5 F; WEEK 10 T to WEEK 10 W
4.4 | View Game Page | Bhimraj Parihar, Siddharth Chhoriya | 2023-02-11 | 2023-02-17 | 1 | 100% | bar: WEEK 5 R to WEEK 5 F; WEEK 10 T to WEEK 10 R
4.5 | Alphabet Training | Bhimraj Parihar, Siddharth Chhoriya | 2023-02-18 | 2023-02-24 | 1 | 100% | bar: WEEK 5 R to WEEK 5 F; WEEK 10 T to WEEK 10 F
4.6 | Math Quiz | Bhimraj Parihar, Siddharth Chhoriya | 2023-02-25 | 2023-03-02 | 1 | 100% | bar: WEEK 5 R to WEEK 5 F; WEEK 10 F to WEEK 11 M
4.7 | Settings | Bhimraj Parihar, Siddharth Chhoriya | 2023-03-03 | 2023-03-09 | 1 | 100% | bar: WEEK 5 R to WEEK 5 F; WEEK 10 F to WEEK 11 T
4.8 | Drawing pad | Bhimraj Parihar, Siddharth Chhoriya | 2023-03-10 | 2023-03-16 | 1 | 100% | bar: WEEK 5 R to WEEK 5 F; WEEK 11 T to WEEK 11 W
4.9 | Game With Sound | Bhimraj Parihar, Siddharth Chhoriya | 2023-03-17 | 2023-03-23 | 1 | 100% | bar: WEEK 5 R to WEEK 5 F; WEEK 11 W to WEEK 11 R
4.1 | Graphical Representation | Bhimraj Parihar, Siddharth Chhoriya |  |  | 0 | 100% | bar: WEEK 5 R to WEEK 5 F; WEEK 11 R to WEEK 11 F
5 | Report Preparation
5.1 | Black Book | Bhimraj Parihar, Siddharth Chhoriya | 2023-03-01 | 2023-04-01 | 1 | 100% | bar: WEEK 5 R to WEEK 5 F; WEEK 12 M to WEEK 12 F
5.2 | PPT | Bhimraj Parihar, Siddharth Chhoriya | 2023-03-01 | 2023-04-01 | 1 | 100% | bar: WEEK 5 R to WEEK 5 F; WEEK 12 M to WEEK 12 F
5.3 | Gantt Chart | Bhimraj Parihar, Siddharth Chhoriya | 2023-05-02 | 2023-05-02 | 1 | 100% | bar: WEEK 5 R to WEEK 5 F; WEEK 12 M to WEEK 12 F