## Table 1
Integrating Recommendation System for Creative Learning Web Framework_Final |  | A.P. Shah Institute of ľechnology
Prof. Geetanjali Kalme | [6 empty] | 2023-05-04
[5 empty] | DURAľION( Weeks) | PCľ OÏ ľASK COMPLEľE | PHASE ONE | [14 empty] | PHASE ľWO | [14 empty] | PHASE ľHREE | [14 empty] | PHASE ÏOUR
WBS NUMBER | ľASK ľIľLE | ľASK OWNER | SľARľ DAľE | DUE DAľE |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | ľ | W | R | Ï | M | ľ | W | R | Ï | M | ľ | W | R | Ï | M | ľ | W | R | Ï | M | ľ | W | R | Ï | M | ľ | W | R | Ï | M | ľ | W | R | Ï | M | ľ | W | R | Ï | M | ľ | W | R | Ï | M | ľ | W | R | Ï | M | ľ | W | R | Ï | M | ľ | W | R | Ï
1 | Píoject Conception and Initiation
1.1 | Research paper search | Ruchita Raut, Kushal Todi, Pratik Dhumal | 2022-07-10 | 18-01-2023 | 3 | 100% | bar: WEEK 1 Ï to WEEK 2 Ï
1.1.1 | Reseaích papeí finalization | Ruchita Raut, Kushal Todi, Pratik Dhumal | 19-01-2022 | 16-02-2023 | 3 | 100%
1.2 | Píoject ľitle | Ruchita Raut | 2022-12-08 | 26-08-2022 | 3 | 100% | bar: WEEK 2 M to WEEK 3 W
1.3 | Abstíact | Kushal Todi | 2022-08-23 | 2022-08-30 | 1 | 100% | bar: WEEK 2 M to WEEK 3 R
1.4 | Objectives | Pratik Dhumal | 2022-08-23 | 2022-08-30 | 1 | 100% | bar: WEEK 2 M to WEEK 3 R
1.5 | Liteíatuíe Review | Ruchita Raut, Kushal Todi | 2019-08-23 | 2022-08-30 | 1 | 100% | bar: WEEK 3 ľ to WEEK 3 R
1.6 | Píoblem Definition | Pratik Dhumal, Kushal Todi | 2022-03-23 | 2022-08-30 | 1 | 100% | bar: WEEK 3 Ï
1.7 | Scope | Kushal Todi | 2022-08-23 | 2022-08-30 | 1 | 100% | bar: WEEK 2 M; WEEK 5 M; WEEK 8 M; WEEK 11 M
1.8 | technology stack | Ruchita Raut, Pratik Dhumal, Kushal Todi | 2022-08-23 | 2022-08-30 | 1 | 100%
1.9 | Benefits foí enviíonment | Ruchita Raut | 2022-08-23 | 2022-08-30 | 1 | 100%
1.1 | Benefits foí society | Pratik Dhumal | 2022-08-23 | 2022-08-30 | 1 | 100%
1.11 | Applications | Kushal Todi | 2022-08-23 | 2022-08-30 | 1 | 100%
2 | Píoject Design
2.1 | Píoposed System | Ruchita Raut | 2022-09-19 | 2022-09-27 | 1 | 100% | bar: WEEK 4 M to WEEK 4 R
2.2 | Design(Flow Of Modules) | Pratik Dhumal | 2022-09-19 | 2022-09-27 | 1 | 100% | bar: WEEK 4 ľ to WEEK 6 R
2.3 | Activity Diagíam | Kushal Todi | 2022-09-19 | 2022-09-27 | 1 | 100% | bar: WEEK 4 R to WEEK 5 Ï
2.4 | Use Case Diagíam | Ruchita Raut | 2022-09-19 | 2022-09-27 | 1 | 100% | bar: WEEK 5 M to WEEK 6 Ï
2.5 | Descíiption Of Use Case | Kushal Todi, Ruchita Raut | 2022-09-19 | 2022-09-27 | 1 | 100% | bar: WEEK 2 M; WEEK 5 M to WEEK 6 Ï; WEEK 8 M; WEEK 11 M
2.6 | Hybrid Recommendation Model | Pratik Dhumal | 2022-09-19 | 2022-09-27 | 1 | 100% | bar: WEEK 5 M to WEEK 5 R
2.6.1 | Collaborative filtering Model | Ruchita Raut | 2022-09-19 | 2022-09-27 | 1 | 100% | bar: WEEK 5 ľ to WEEK 6 Ï
2.6.2 | Setting PostgreSQL | Kushal Todi | 2022-09-19 | 2022-09-27 | 1 | 100% | bar: WEEK 5 W to WEEK 6 R
2.6.3 | Building APIs | Pratik Dhumal | 2022-09-19 | 2022-09-27 | 1 | 100% | bar: WEEK 5 W to WEEK 6 W
2.6.4 | User Interface | Ruchita Raut | 2022-09-19 | 2022-09-27 | 1 | 100% | bar: WEEK 5 W to WEEK 6 Ï
2.7 | Preparation Of Report | Kushal Todi, Ruchita Raut | 2022-09-19 | 2022-09-27 | 1 | 100% | bar: WEEK 5 R; WEEK 6 Ï
3 | Project Implementation
3.1 | Conducted Survey to collect data | Ruchita Raut, Kushal Todi, Pratik Dhumal | 2022-10-01 | 2022-10-10 | 1 | 100% | bar: WEEK 7 M to WEEK 9 M
3.2 | Created Datasets from survey insights | Ruchita Raut | 2022-10-11 | 2022-10-20 | 2 | 100% | bar: WEEK 8 M to WEEK 9 Ï
3.3 | Collaborative filtering Model with Premitive UI | Kushal Todi | 2022-10-21 | 2022-11-21 | 2 | 100% | bar: WEEK 8 M to WEEK 9 Ï
3.4 | Hybrid Recommedation Model with Final UI | Pratik Dhumal | 2022-12-22 | 2022-12-30 | 2 | 100% | bar: WEEK 7 R to WEEK 9 Ï
4 | ľesting
4.1 | Design of ľest Cases | Pratik Dhumal | 2023-01-07 | 2023-01-24 | 3 | 100% | bar: WEEK 10 M
4.2 | Testing Header Component ľest | Kushal Todi, Pratik Dhumal | 2023-01-27 | 2023-02-03 | 1 | 100% | bar: WEEK 10 M to WEEK 10 ľ
4.3 | Testing category creation API ľest | Ruchita Raut | 2023-02-04 | 2023-02-10 | 1 | 100% | bar: WEEK 10 ľ to WEEK 10 W
4.4 | Testing add Rating API ľest | Pratik Dhumal | 2023-02-11 | 2023-02-17 | 1 | 100% | bar: WEEK 10 ľ to WEEK 10 R
4.5 | Testing ModelOutput API ľest | Kushal Todi | 2023-02-18 | 2023-02-24 | 1 | 100% | bar: WEEK 10 ľ to WEEK 11 Ï
4.6 | Testing Signup Component ľest | Pratik Dhumal | 2023-02-25 | 2023-03-02 | 1 | 100% | bar: WEEK 10 R to WEEK 11 Ï
4.7 | Testing Login Component ľest | Pratik Dhumal | 2023-03-03 | 2023-03-09 | 1 | 100% | bar: WEEK 10 Ï to WEEK 11 Ï
4.8 | Testing Productard Component ľest | Kushal Todi, Ruchita Raut | 2023-03-10 | 2023-03-16 | 1 | 100%
4.9 | Testing ProductDeatils Component ľest | Ruchita Raut | 2023-03-17 | 2023-03-23 | 1 | 100%
4.1 | Testing Checkout Component ľest | Kushal Todi | 2023-03-24 | 2023-03-30 | 1 | 100%
5.1 | Report Preparation