## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE- Agrolife: ML enabled Plant Disease Classification System | [6 empty] | INSTITUTE & DEPARTMENT NAME | [6 empty] | A P Shah Institute of Technology, Department of Information Technology
PROJECT GUIDE- Dr. Sameer Nanivadekar, Prof. Sonal Jain, Prof. Charul Singh | [6 empty] | DATE | [6 empty] | 2023-05-04
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Research paper search | Anagha | 2022-07-10 | 2022-07-26 | 3 | 100% | bar: WEEK 1 F to WEEK 2 T
1.1.1 | Research paper finalization | Ishika | 2022-07-10 | 2022-07-26 | 3 | 100% | bar: WEEK 2 W
1.2 | Project Title | Anagha,Ishika, Ruta | 2022-07-10 | 2022-07-26 | 3 | 100% | bar: WEEK 2 W to WEEK 3 W
1.3 | Abstract | Ruta | 2022-08-23 | 2022-08-30 | 1 | 100% | bar: WEEK 2 R to WEEK 3 R
1.4 | Objectives | Ishika | 2022-08-23 | 2022-08-30 | 1 | 100% | bar: WEEK 3 M to WEEK 3 R
1.5 | Literature Review | Ruta | 2022-08-23 | 2022-08-30 | 1 | 100% | bar: WEEK 3 T to WEEK 3 R
1.6 | Problem Definition | Anagha, Ishika, Ruta | 2022-03-23 | 2022-08-30 | 1 | 100% | bar: WEEK 3 F
1.7 | Scope | Anagha | 2022-08-23 | 2022-08-30 | 1 | 100% | bar: WEEK 3 F
1.8 | Technology stack | Anagha, Ishika, Ruta | 2022-08-23 | 2022-08-30 | 1 | 80% | bar: WEEK 3 F
1.9 | Benefits for environment | Anagha | 2022-08-23 | 2022-08-30 | 1 | 100% | bar: WEEK 3 F
1.1 | Benefits for society | Ishika | 2022-08-23 | 2022-08-30 | 1 | 80% | bar: WEEK 3 F
1.11 | Applications | Ruta | 2022-08-23 | 2022-08-30 | 1 | 100% | bar: WEEK 3 F
2 | Project Design
2.1 | Proposed System | Anagha, Ishika, Ruta | 2022-09-19 | 2022-09-27 | 1 | 70% | bar: WEEK 4 M to WEEK 4 R
2.2 | Design(Flow Of Modules) | Anagha | 2022-09-19 | 2022-09-27 | 1 | 70% | bar: WEEK 4 F to WEEK 5 F
2.3 | Activity Diagram | Ruta | 2022-09-19 | 2022-09-27 | 1 | 50%
2.4 | Use Case Diagram | Ishika | 2022-09-19 | 2022-09-27 | 1 | 50%
2.5 | Description Of Use Case | Ishika | 2022-09-19 | 2022-09-27 | 1 | 30%
2.6 | Modules | Anagha, Ishika, Ruta | 2022-09-19 | 2022-09-27 | 1
2.6.1 | Plant disease classification module | Anagha | 2022-09-19 | 2022-09-27 | 1
2.6.2 | Fertilizer Recommendation module | Ruta | 2022-09-19 | 2022-09-27 | 1
2.6.3 | Crop Recommendation module | Ishika | 2022-09-19 | 2022-09-27 | 1
2.6.4 | Total workflow of project | Anagha, Ishika, Ruta | 2022-09-19 | 2022-09-27 | 1
2.7 | Preparation Of Report | Ruta | 2022-09-19 | 2022-09-27 | 1
3 | Project Implementation
3.1 | Plant disease classification module | Anagha | 3-16-23 | 3-23-23 | 1 | 100%
3.2 | Fertilizer Recommendation module | Ruta, Ishika | 3-23-23 | 2023-04-01 | 2 | 80%
3.3 | Crop Recommendation module | Ishika, Anagha | 2023-05-04 | 2023-04-12 | 1 | 100%
3.4 | Integration of all modules | Anagha, Ruta | 4-13-23 | 4-20-23 | 1 | 100%
4 | Testing
4.1 | Design of Test Cases | Anagha, Ishika, Ruta | 2023-01-07 | 2023-01-24 | 3 | 0% | bar: WEEK 1 T to WEEK 1 F; WEEK 2 T to WEEK 2 F; WEEK 3 T to WEEK 3 F
4.2 |  | Anagha, Ishika, Ruta | 2023-01-27 | 2023-02-03 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.3 |  | Anagha, Ishika, Ruta | 2023-02-04 | 2023-02-10 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.4 |  | Anagha, Ishika, Ruta | 2023-02-11 | 2023-02-17 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.5 |  | Anagha, Ishika, Ruta | 2023-02-18 | 2023-02-24 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.6 |  | Anagha, Ishika, Ruta | 2023-02-25 | 2023-03-02 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.7 |  | Anagha, Ishika, Ruta | 2023-03-03 | 2023-03-09 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.8 |  | Anagha, Ishika, Ruta | 2023-03-10 | 2023-03-16 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.9 |  | Anagha, Ishika, Ruta | 2023-03-17 | 2023-03-23 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.1 |  | Anagha, Ishika, Ruta | 2023-03-24 | 2023-03-30 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.1 |  | Anagha, Ishika, Ruta | 2023-03-31 | 2023-04-06 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.1 |  | Anagha, Ishika, Ruta | 2023-04-07 | 2023-04-13 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.1 |  | Anagha, Ishika, Ruta | 2023-04-14 | 2023-04-20 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.1 |  | Anagha, Ishika, Ruta | 2023-04-21 | 2023-04-27 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.1 |  | Anagha, Ishika, Ruta | 2023-04-21 | 2023-04-27 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.1 |  | Anagha, Ishika, Ruta | 2023-04-28 | 2023-05-04 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.1 |  | Anagha, Ishika, Ruta | 2023-04-29 | 2023-05-05 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.1 |  | Anagha, Ishika, Ruta | 2023-04-30 | 2023-05-06 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.1 |  | Anagha, Ishika, Ruta | 2023-05-01 | 2023-05-07 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.1 |  | Anagha, Ishika, Ruta | 2023-05-02 | 2023-05-08 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
5.2 | Graphical Representation | Ishika |  |  | 0 | 0%
5.3 | Report Preparation | Anagha, Ishika, Ruta